## Tabelle1
Risk Management

Name	Description	Probability	Impact	Factor	Mitigation	Responsible
Changes to the Blizzard API	Major API changes to the blizzard API	unknown	very high	25 %	Subscribing to the RSS feed, to get updates on API changes	Leon Gottschick
Compatibility problems between each Project	We have split GottMusIg into 3 Projects	unlikely	very high	25 %	Integration Tests	Kamil Kalmus, Leon Gottschick, Christoph Emig
SimulationCraft API changes	Major API changes to SimulationCraft	unlikely	very high	20 %	read developer updates on the website	Christoph Emig
Deadline Pressure	We dont finish until July	likely	low	10 %	keep the deadline in mind	Everyone
Framework compatibility	Many transient dependencies	medium	medium	10 %	Update versions only after communicating it	Everyone
We need more time for our project as expected	A similar project is released before we can release ours	low	medium	5 %	First release with less features	Everyone
API Key not sufficient	We have 6000 requests per hour	low	very high	5 %	create several accounts for backup	Kamil Kalmus, Leon Gottschick