## Tabelle1
Risk Management
| Name | Description | Propability | Impact | Factor | Mitigation | Responsible
| Changes to the Blizzard API | Major API changes to the blizzard API | unknown | very high | 25% | Subscribing to the RSS feed, to get updates on API changes | Leon Gottschick
| SimulationCraft API changes | Major API changes to SimulationCraft | unlikely | very high | 20% | read developer updates on the website | Christoph Emig
| Database goes down | Database on an external hoster | unlikely | very high | 20% | host on homeserver | Kamil Kalmus, Leon Gottschick
| Deadline Pressure | We dont finish until July | likely | low | 10% | keep the deadline in mind | Everyone
| Framework compatibility | Many transient dependencies | medium | medium | 10% | Update versions only after communicating it | Everyone
| SimulationCraft needs too much resources | Too much cpu and ram load | high | medium | 10% | Host on powerful server | Christoph Emig
| API Key not sufficient | We have 6000 requests per hour | low | very high | 5% | create several accounts for backup | Kamil Kalmus, Leon Gottschick