## Tabelle1
UC Name | Documentation | UI Design | Database | Warmup Phase | Coding | Testing | Total w/o warmup | Total | Estimate | FP | Explaniation
DPSDifference | 1:00 | 0:00 | 0:30 | 0:00 | 0:20 | 0:10 | 2:00 | 2:00 | 2:49 | 11.05
Search Character | 1:00 | 0:10 | 0:30 | 0:00 | 1:00 | 0:30 | 3:10 | 3:10 | 3:29 | 13.65
Login | 1:00 | 0:30 | 0:30 | 3:00 | 1:30 | 1:00 | 4:30 | 7:30 | 3:58 | 15.6
Show Character | 1:00 | 1:30 | 0:30 | 2:30 | 2:00 | 0:20 | 5:20 | 7:50 | 4:27 | 17.5 | CSS with Vaadin, complete recode
Update Character | 1:00 | 0:30 | 0:10 | 0:00 | 1:30 | 0:30 | 3:40 | 3:40 | 3:29 | 13.65
Update Database | 1:00 | 1:30 | 0:30 | 0:00 | 0:30 | 0:40 | 4:10 | 4:10 | 4:38 | 18.2
DPSDifference | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 0 | 1 | 0 | 0 | 0 | 0 | 0 | User only reads | 13.65
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 0 | 1 | 4
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 0 | 1 | 3
Number of Files (ILF) | 2 | 1 | 0 | 0 | 0 | 1 | 14 | Presenter, Bar Model |  |  |  | Time spent (w/o outliers) | Function Points (w/o outliers) | Velocity
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Google retuns a lot of information |  |  |  | 22.8333 | 89.65 | 3.9263
Search Character | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 0 | 1 | 0 | 0 | 0 | 0 | 0 | User only asks to login | 15.6
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 0 | 2 | 3 | User sends username and password
Number of Files (ILF) | 3 | 1 | 0 | 0 | 0 | 0 | 21 | The window, the UI, the User model
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0 | No communication to the outside
Login | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 13.65
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 0 | 2 | 4
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 0 | 1 | 3
Number of Files (ILF) | 2 | 1 | 0 | 0 | 0 | 2 | 14 | Presenter, Bar
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Show Character | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 18.2
Number of User Outputs (EO) | 1 | 1 | 0 | 0 | 0 | 5 | 4
Number of User Inquiries (EQ) | 1 | 1 | 0 | 0 | 2 | 0 | 3
Number of Files (ILF) | 3 | 1 | 0 | 0 | 0 | 0 | 21 | View, Presenter, Database, Model,
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Update Character | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 0 | 1 | 0 | 1 | 25 | 4 | 25 single, clickable stars | 17.5
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of Files (ILF) | 3 | 1 | 0 | 0 | 1 | 11 | 21 | Presenter, Rating Class, Bar Class. Influences many fields in the database
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Update Database | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 1 | 1 | 0 | 0 | 0 | 1 | 3 |  | 11.05
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of Files (ILF) | 2 | 1 | 0 | 0 | 0 | 0 | 14 | Presenter, Bar model
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Name | Count | Simple | Average | Complex | FTR/RET | DET | Points | Reason | Function points
Number of User Input (Ei) | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0
Number of User Outputs (EO) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of User Inquiries (EQ) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of Files (ILF) | 0 | 1 | 0 | 0 | 0 | 0 | 0
Number of External Interfaces (EIF) | 0 | 1 | 0 | 0 | 0 | 0 | 0